## Instructions
We will use Excel
· First tab is your Project Plan Make sure you state the Project Name (name of the technology solution)
· Second tab is Resources which is list of your team members and what skills they bring to the project.
Project Plan
Tasks - can add new tasks to provide more detail (remember to use a verb for example: Create Dashboard Wireframe, Create virtual server in AWS)
% completed
Start Date - this is your planned date and eventually will change to your actual date.
Finish Date - this may change as you realize that some tasks take longer than others. You put in the comments that the date changed and why.
Resource Name is the person who responsible to get this done. It may be a team who is working on it, yet there is one person who is leading the effort.
Notes - comments which explain the updates to the plan (i.e.. problems, accomplishments)

## Capstone Project Plan
| Task Name | % Complete | Start | Finish | Resource Name | Notes
Phase | Project Name: CloudEx
1 | SYSTEMS DESIGN
| Process Map | 100% | 2025-09-07 | 2025-09-10 | Zuriel Bagui | Drafted logical process map
| Create User Interface (mockup) | 100% | 2025-09-11 | 2025-09-13 | Zuriel Bagui
| Create Infratructure Architecture (Network Topology) | 100% | 2025-09-11 | 2025-09-13 | Stanco Diaz
| Create Information Architecture (ERD) | 100% | 2025-09-11 | 2025-09-13 | Pallav Pokhrel
2 | SYSTEMS DEVELOPMENT
| Establish Development Environment |  |  |  | Zuriel Bagui
| Setup Shared Folder/ Version Control | 100% | 2025-09-15 | 2025-09-16 | Zuriel Bagui
Configure Git
| Install required software | 100% | 2025-09-15 | 2025-09-16 | Zuriel Bagui
| Create environment config | 100% | 2025-09-16 | 2025-09-17 | Zuriel Bagui
| Create User interface (webpages) |  |  |  | Stanco Diaz
| Build login page | 0% | 2025-10-02 | 2025-10-06 | Stanco Diaz
| Build stock list page | 0% | 2025-10-08 | 2025-10-13 | Stanco Diaz
| Build portfolio dashboard | 0% | 2025-10-10 | 2025-10-15 | Stanco Diaz
| Build transaction history page | 0% | 2025-10-20 | 2025-10-24 | Zuriel Bagui
| Build admin panel | 0% | 2025-10-25 | 2025-10-30 | Zuriel Bagui
| Create Application |  |  |  | Stanco Diaz
| Implement buy order | 0% | 2025-10-02 | 2025-10-07 | Stanco Diaz
| Implement sell order | 0% | 2025-10-08 | 2025-10-12 | Stanco Diaz
| Implement deposits and withdrawals | 0% | 2025-10-08 | 2025-10-12 | Stanco Diaz
| Implement order cancellation | 0% | 2025-10-27 | 2025-10-31 | Pallav Pokhrel
| Apply market hours restrictions | 0% | 2025-11-01 | 2025-11-05 | Zuriel Bagui
| Create Database |  |  |  | Pallav Pokhrel
| Provision AWS RDS PostgreSQL | 0% | 2025-09-18 | 2025-09-19 | Zuriel Bagui
| Build core tables | 0% | 2025-09-20 | 2025-09-23 | Pallav Pokhrel
| Build transaction tables | 0% | 2025-09-24 | 2025-09-26 | Pallav Pokhrel
| Test queries | 0% | 2025-09-27 | 2025-09-29 | Stanco Diaz
| Deploy on cloud provider (AWS) |  |  |  | Pallav Pokhrel
| Create elastic beanstalk API | 0% | 2025-11-03 | 2025-11-07 | Pallav Pokhrel
| Configure S3 + CloudFront | 0% | 2025-11-08 | 2025-11-12 | Pallav Pokhrel
| Setup cognito authorization | 0% | 2025-09-25 | 2025-10-01 | Zuriel Bagui
| Implement price generator (Lambda + EventBrdige) | 0% | 2025-11-13 | 2025-11-17 | Pallav Pokhrel
| Test system integration | 0% | 2025-11-18 | 2025-11-22 | Zuriel Bagui
Documentation
| Mid-Build Deck | 0% | 2025-10-19 | 2025-10-25 | Zuriel Bagui
| Build 1 Video | 0% | 2025-10-19 | 2025-10-25 | Stanco Diaz
| Final Build Deck | 0% | 2025-11-23 | 2025-11-29 | Pallav Pokhrel
| Final Build Video | 0% | 2025-11-23 | 2025-11-29 | Pallav Pokhrel
| Create Showcase Presentation | 0% | 2025-11-25 | 2025-11-30 | Zuriel Bagui

## Resources
Project Name: CloudEX | Resources which is list of your team members and what skills they bring to the project.
Team Member | Skills | Notes
Zuriel Bagui | Network configuration and management
Systems administration
Automation and scripting for IT process efficiency
Computer troubleshooting and technical support
Collaboration with web developers on design, usability, and functionality improvements
Project coordination and cross-team communication
Stanco Diaz | Full-Stack Development: JavaScript, TypeScript, React, Next.js, Node.js, Express.js
Database Management: SQL
API Integration: REST APIs
Tools & Systems: Git, Linux, and Bash
General Experience: Web and mobile app deployment, project collaboration
Object-Oriented Programming (OOP)
Pallav Pokhrel | Automation: Python & Powershell
System Admin
Project Management & Collaboration
Backend Database Creation/Management: SQL, .NET
Basic UX/UI Design
OS Administration: Windows, MacOS, Linux
Presentations: Powerpoint & Google Slides
Cloud Management: Azure & AWS(mainly Azure but have taken multiple AWS courses)